## Sheet1
Project Selection |  |  |  | Software Design | Implementation
Start: 1/11/2016 | Requirements Report | Requirements Report | Requirements Report | Start: 2/17/2016 | Start: 3/28/2016
End: 1/22/2016 | Introduction | Project Plan | Reuirements | End: 3/28/2016 | End: 4/22/2016
| Start: 1/22/2016 | Start: 2/06/2016 | Start: 2/06/2016
Group Selecction | End: 1/22/2016 | End: 2/10/2016 | End: 2/10/2016 | Testing Design | Testing
Start: 1/11/2016 |  |  |  | Start: 2/17/2016 | Start: 3/28/2016
End: 1/22/2016 |  |  |  | End: 3/28/2016 | End: 4/22/2016